## Sheet1
Risks | Category | Probability | Impact | Impact Values
Product may not be completed in time | PS | 90% | 1 | 1 | Catastrophic
Allocated tasks may not be syncronized in time | TE | 80% | 2 | 2 | Critical
End users resist system | BU | 70% | 2 | 3 | Marginal
Functionalities may not integrate well together | TE | 50% | 2 | 4 | Negligible
Product may not stand out in the market | BU | 60% | 2
Development team may lack the appropirate knowledge and tools for implementation | DE | 20% | 3
Requirements may change during development | PS | 50% | 3
Product functionality design may not cover all customer needs | BU | 50% | 2
Product interface may not be user-friendly | DE | 30% | 3
Documentation may lack detail | DE | 50% | 2
Larger number of users than planned | PS | 30% | 3